## Read Me
HotelERP - QA status, module by module
Complete menu and submenu coverage, findings, fixes, and the go-live sequence. Every figure is either a formula or traceable to a file in the repository.
WHAT WAS DONE
Scope | All 60 pages (3 menus + 57 submenus) across 5 modules, all 5 roles, 6 backend services and the SPA.
Live testing | ~2,860 API calls against the staging deployment: 1,728 reads (144 endpoints x 5 roles x 2 surfaces) and 1,010 write probes (159 paths x 5 roles).
Live page sweep | 60/60 routes rendered with live data. 0 console errors, 0 failed requests, 0 broken images, 0 layout overflow.
Regression | 37 suites, 1,268 pytest assertions plus 73 checks in the 4 script suites, 0 failures. Identical results under ROUTE_POLICY_MODE=audit (the shipped default) and enforce.
Lint | ESLint: 0 errors, 10 warnings (unchanged baseline).
HOW TO READ THE STATUS COLUMNS
Done / Fixed in source | A defect was found against this module, the fix is in the working tree, and a test that fails without the fix now passes. NOT yet on the deployment.
Needs deploy | The fix is in the working tree but ships disabled or unactivated. Still live as a finding until it is deployed.
No defect found | Tested, and nothing came up. This is NOT the same claim as 'verified perfect' - it means no test detected a problem, not that none exists.
Open | A real defect that is still present. No fix, or a fix that cannot be made in source.
Owner decision | Deliberately not changed here. The right answer depends on the business, not on the code.
THE ONE THING TO KNOW BEFORE TRUSTING IT
Not deployed | The fixes are in the working tree. Nothing is committed or pushed. Every fix is proven by unit tests and by regenerating the permission map byte-identically - NOT by a request against the running system. Step 11 of Go-Live closes that gap.
KNOWN LIMITS OF THIS AUDIT
Frontend build | npm run build could not run on the QA machine (@oxc-resolver's win32 binding fails ERR_DLOPEN_FAILED). Frontend changes are verified by ESLint and by Node-level HTTP tests only.
Scope of destructive testing | No DoS, no real payments, emails or SMS, no deletion of business records, no database resets. Write probes used record id 999999999, which cannot exist.
One process defect | An early probe of this audit issued DELETE against real ids expecting a 403. It was not refused, and two rows were deleted (a tax, and Room 601's photos). Both were restored. Recorded in QA/live/FINDINGS.md rather than quietly fixed.
Passwords | No credential appears anywhere in this workbook or in the repository's working tree. The value is supplied at seed time via SEED_PASSWORD.

## Module Status
Module status - done, pending, and what is still open
One row per module. Page and finding counts are formulas over the 'Menu & Submenu Status' and 'Findings' tabs.
Module | Owning service | Pages | Routes | Test suites | Checks | Findings | Status
Hotel / Reservations | HotelServices :9005 |  |  |  |  | QA-BIZ-001 Fixed in source; QA-BIZ-002 Fixed in source; QA-SEC-006 Owner decision; QA-SEC-009 Open (module-wide) | Needs deploy
Master Data | MasterDataServices :9015 |  |  |  |  | QA-SEC-002 Fixed in source (module-wide); QA-SEC-007 Fixed in source (module-wide) | Fixed in source
Restaurant (F&B) | RestaurantServices :9030 |  |  |  |  | QA-SEC-002 Fixed in source (module-wide); QA-BIZ-003 Pass | Fixed in source
Bar | BarServices :9025 |  |  |  |  | QA-SEC-002 Fixed in source (module-wide); QA-BIZ-003 Pass | Fixed in source
HRM / Users | UserServices :9020 |  |  |  |  | QA-SEC-001 Fixed in source (module-wide); QA-DATA-001 Open | Open
Cross-module (SPA) | Frontend SPA (aggregates every service) |  |  |  |  | QA-SEC-005 Fixed in source; QA-UX-002 Fixed in source | Fixed in source
Cross-cutting (build & deploy) | repo root / deployment host |  |  |  |  | QA-SEC-004 Open (module-wide); QA-SEC-001b Needs deploy (module-wide); QA-SEC-008 Partial (module-wide); QA-UX-003 Fixed in source (module-wide) | Needs deploy
TOTAL
Test suites by module
Module | Suite | Checks
Hotel / Reservations | test_night_audit.py | 50
Hotel / Reservations | test_reservation_rules.py | 111
Hotel / Reservations | test_reservation_pricing.py | 10
Hotel / Reservations | test_booking_validation.py | 24
Hotel / Reservations | test_reservation_housekeeping.py | 23
Hotel / Reservations | test_master_client.py | 45
Hotel / Reservations | test_upload_content.py | 78
Hotel / Reservations | test_phone_validation.py | 120
Hotel / Reservations | test_phone_pattern_guard.py | 2
Hotel / Reservations | test_jwt_auth.py | 10
Master Data | test_snapshot_contract.py | 12
Master Data | test_upload_content.py | 65
Master Data | test_jwt_auth.py | 10
Restaurant (F&B) | test_bill_payment.py | 11
Restaurant (F&B) | test_upload_content.py | 65
Restaurant (F&B) | test_phone_validation.py | 120
Restaurant (F&B) | test_combo_rules.py | 4
Restaurant (F&B) | test_fnb_hardening.py | 6
Restaurant (F&B) | test_jwt_auth.py | 10
Bar | test_bill_payment.py | 11
Bar | test_upload_content.py | 65
Bar | test_phone_validation.py | 120
Bar | test_fnb_hardening.py | 6
Bar | test_jwt_auth.py | 10
HRM / Users | test_rbac.py | 19
HRM / Users | test_user_photo_upload.py | 15
HRM / Users | test_phone_validation.py | 120
HRM / Users | test_jwt_auth.py | 10
Cross-cutting (build & deploy) | test_rbac_gateway.py | 71
Cross-cutting (build & deploy) | test_route_policy.py | 18
Cross-cutting (build & deploy) | test_preflight_images.py | 7
Cross-cutting (build & deploy) | test_seed_night_audit.py | 10
Cross-cutting (build & deploy) | test_jwt_auth.py | 10
Cross-cutting (build & deploy) | test_bind_guard.py | 41
Cross-cutting (build & deploy) | test_spa_fallback.py | 21
Cross-cutting (build & deploy) | install_bind_guard.py | 5
Cross-cutting (build & deploy) | remove_frozen_dates.py | 6

## Menu & Submenu Status
Every menu and submenu, with its status
All 60 pages from the shipped database. V/A/E/D are what each role is granted on that page. 'Reachable' is a formula over those five columns. 'Owning module' is which menu the screen sits under; 'Served by' is which services answer for it - two different questions, and the first attempt conflated them.
# | Kind | Parent menu | Label | Owning module | Path | Served by | Routes | Roles | Admin | F.O. Manager | Front Desk | Housekeeping | F&B | Reachable | QA status | Note
1 | Menu | - | Dashboard | Cross-module (SPA) | /dashboard | Bar, Hotel / Reservations, Master Data, Restaurant (F&B) | 19 | 5 | V/C/E/D | V | V | V | V |  | Fixed in source | QA-SEC-005 fixed: no longer reads guest PII from user_activity_log.
2 | Menu | - | Reservation | Hotel / Reservations | /reservation | Hotel / Reservations, Master Data | 22 | 4 | V/C/E/D | V/C/E/D | V/C/E | V | - |  | Needs deploy | Parent screen; 4 children.
3 | Submenu | Reservation | Add New Reservation | Hotel / Reservations | /add_new_reservation | Hotel / Reservations, Master Data | 14 | 4 | V/C/E/D | V/C/E/D | V/C/E | V | - |  | Needs deploy | QA-BIZ-002 fixed: quote refuses unsellable rooms.
4 | Submenu | Reservation | Booking | Hotel / Reservations | /booking | Hotel / Reservations, Master Data | 7 | 4 | V/C/E/D | V/C/E/D | V/C/E | V | - |  | Needs deploy | QA-SEC-006: Housekeeping granted view here.
5 | Submenu | Reservation | Room View | Hotel / Reservations | /room_view | Master Data | 3 | 4 | V/C/E/D | V/C/E/D | V/C/E | V | - |  | Needs deploy
6 | Submenu | Reservation | Reservation View | Hotel / Reservations | /reservation_view | Hotel / Reservations, Master Data | 2 | 4 | V/C/E/D | V/C/E/D | V/C/E | V | - |  | Needs deploy | QA-BIZ-001 fixed: repeat cancel is a 409.
7 | Submenu | Night Audit | Night Audit | Hotel / Reservations | /night_audit | Hotel / Reservations, Master Data | 5 | 2 | V/C/E/D | V/C/E | - | - | - |  | Needs deploy | QA-SEC-009: business_date comes from the host clock.
8 | Submenu | Night Audit | User Reserved Details | Hotel / Reservations | /user_reserved_details | Hotel / Reservations, Master Data | 3 | 2 | V/C/E/D | V/C/E | - | - | - |  | Needs deploy
9 | Submenu | Night Audit | Room Booked Details | Hotel / Reservations | /room_booked_details | Hotel / Reservations, Master Data | 2 | 2 | V/C/E/D | V/C/E | - | - | - |  | Needs deploy
10 | Submenu | Night Audit | Settlement Summary | Hotel / Reservations | /settlement_summary | Hotel / Reservations, Master Data | 2 | 2 | V/C/E/D | V/C/E | - | - | - |  | Needs deploy
11 | Menu | - | Guest Enquiry | Hotel / Reservations | /guest_enquiry | Hotel / Reservations, Master Data | 7 | 3 | V/C/E/D | V/C/E | V/C/E | - | - |  | Needs deploy
12 | Submenu | House Keeper | Task Assign | Hotel / Reservations | /task_assign | HRM / Users, Hotel / Reservations, Master Data | 10 | 3 | V/C/E/D | V | - | V/C/E | - |  | Needs deploy
13 | Submenu | House Keeper | Room Incident Log | Hotel / Reservations | /room_incident_log | HRM / Users, Hotel / Reservations, Master Data | 10 | 3 | V/C/E/D | V | - | V/C/E | - |  | Needs deploy
14 | Submenu | HRM | Employee | HRM / Users | /employee | HRM / Users, Master Data | 11 | 1 | V/C/E/D | - | - | - | - |  | Open
15 | Submenu | HRM | User | HRM / Users | /user | HRM / Users | 3 | 1 | V/C/E/D | - | - | - | - |  | Open | Only role in the product refused unauthenticated reads (401).
16 | Submenu | HRM | Roles | HRM / Users | /roles | HRM / Users | 4 | 1 | V/C/E/D | - | - | - | - |  | Open | QA-DATA-001: 9 test-harness roles are visible on this screen.
17 | Submenu | HRM | Department | HRM / Users | /department | HRM / Users | 4 | 1 | V/C/E/D | - | - | - | - |  | Open
18 | Submenu | HRM | Designation | HRM / Users | /designation | HRM / Users | 4 | 1 | V/C/E/D | - | - | - | - |  | Open
19 | Submenu | HRM | Shift | HRM / Users | /shift | HRM / Users | 4 | 1 | V/C/E/D | - | - | - | - |  | Open
20 | Submenu | HRM | Restaurant Roster | HRM / Users | /restaurant_roster | HRM / Users, Restaurant (F&B) | 5 | 1 | V/C/E/D | - | - | - | - |  | Open
21 | Submenu | HRM | Restaurant Shift Planning | HRM / Users | /restaurant_shift_planning | HRM / Users, Restaurant (F&B) | 9 | 1 | V/C/E/D | - | - | - | - |  | Open
22 | Submenu | HRM | Bar Roster | HRM / Users | /bar_roster | Bar, HRM / Users | 5 | 1 | V/C/E/D | - | - | - | - |  | Open
23 | Submenu | HRM | Bar Shift Planning | HRM / Users | /bar_shift_planning | Bar, HRM / Users | 9 | 1 | V/C/E/D | - | - | - | - |  | Open
24 | Submenu | Restaurant | Menu Management | Restaurant (F&B) | /menus | Restaurant (F&B) | 16 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
25 | Submenu | Restaurant | Combo / Package Deals | Restaurant (F&B) | /combo_deals | Restaurant (F&B) | 5 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
26 | Submenu | Restaurant | Floor Layout | Restaurant (F&B) | /floor_layout | Restaurant (F&B) | 4 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
27 | Submenu | Restaurant | Table Master | Restaurant (F&B) | /table_master | Restaurant (F&B) | 5 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
28 | Submenu | Restaurant | Order Management | Restaurant (F&B) | /orders | Restaurant (F&B) | 9 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
29 | Submenu | Restaurant | Table Reservation | Restaurant (F&B) | /table_reservation | Restaurant (F&B) | 4 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
30 | Submenu | Restaurant | Main Kitchen | Restaurant (F&B) | /kot/main_kitchen | Restaurant (F&B) | 6 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
31 | Submenu | Restaurant | Grill Kitchen | Restaurant (F&B) | /kot/grill | Restaurant (F&B) | 6 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
32 | Submenu | Restaurant | Dessert Kitchen | Restaurant (F&B) | /kot/dessert | Restaurant (F&B) | 6 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
33 | Submenu | Restaurant | Billing & Payments | Restaurant (F&B) | /billing_payments | Restaurant (F&B) | 9 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
34 | Submenu | Restaurant | Inventory Control | Restaurant (F&B) | /stock | Restaurant (F&B) | 5 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
35 | Submenu | Restaurant | Recipe Management | Restaurant (F&B) | /recipe_management | Restaurant (F&B) | 6 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
36 | Submenu | Restaurant | Guest Management | Restaurant (F&B) | /guest_management | Restaurant (F&B) | 8 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
37 | Submenu | Restaurant | Report & Analytics | Restaurant (F&B) | /reports_analytics | Restaurant (F&B) | 8 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
38 | Submenu | Bar | Menu Management | Bar | /bar_menus | Bar | 16 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
39 | Submenu | Bar | Floor Layout | Bar | /bar_floor_layout | Bar | 4 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
40 | Submenu | Bar | Table Master | Bar | /bar_table_master | Bar | 5 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
41 | Submenu | Bar | Order Management | Bar | /bar_orders | Bar | 9 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
42 | Submenu | Bar | Station Display | Bar | /bar_station | Bar | 7 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
43 | Submenu | Bar | Billing & Payments | Bar | /bar_billing_payments | Bar | 9 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
44 | Submenu | Bar | Stock | Bar | /bar_stock | Bar | 5 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
45 | Submenu | Bar | Recipe Management | Bar | /bar_recipe_management | Bar | 6 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
46 | Submenu | Bar | Guest Management | Bar | /bar_guest_management | Bar | 8 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
47 | Submenu | Bar | Report & Analytics | Bar | /bar_reports_analytics | Bar | 8 | 2 | V/C/E/D | - | - | - | V/C/E |  | Fixed in source
48 | Submenu | Master Data | Facilities | Master Data | /facilities | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
49 | Submenu | Master Data | Room Type | Master Data | /room_type | Master Data | 6 | 2 | V/C/E/D | V | - | - | - |  | No defect found
50 | Submenu | Master Data | Bed Type | Master Data | /bed_type | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
51 | Submenu | Master Data | Hall / Floor | Master Data | /hall_floor | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
52 | Submenu | Master Data | Rooms | Master Data | /rooms | Master Data | 8 | 2 | V/C/E/D | V | - | - | - |  | No defect found
53 | Submenu | Master Data | Discount Type | Master Data | /discount_type | Master Data | 5 | 2 | V/C/E/D | V | - | - | - |  | No defect found
54 | Submenu | Master Data | Tax Types | Master Data | /tax_types | Master Data | 5 | 2 | V/C/E/D | V | - | - | - |  | No defect found
55 | Submenu | Master Data | Payment Methods | Master Data | /payment_methods | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
56 | Submenu | Master Data | Identification Proof | Master Data | /identification_proof | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
57 | Submenu | Master Data | Currency & Country | Master Data | /currency_country | Master Data | 5 | 2 | V/C/E/D | V | - | - | - |  | No defect found
58 | Submenu | Master Data | HSK Task Type | Master Data | /hsk_task_type | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
59 | Submenu | Master Data | Complementary | Master Data | /complementary | Master Data | 5 | 2 | V/C/E/D | V | - | - | - |  | No defect found
60 | Submenu | Master Data | Reservation Status | Master Data | /reservation_status | Master Data | 4 | 2 | V/C/E/D | V | - | - | - |  | No defect found
TOTALS |  |  |  |  | pages | routes

## Role Access Matrix
Role access, as the database actually grants it
V/A/E/D = view / add / edit / delete. This is the permission data itself, not a re-derivation. Column totals are formulas.
# | Label | Path | Admin | F.O. Manager | Front Desk | Housekeeping | F&B
1 | Dashboard | /dashboard | V/C/E/D | V | V | V | V
2 | Reservation | /reservation | V/C/E/D | V/C/E/D | V/C/E | V | -
3 | Add New Reservation | /add_new_reservation | V/C/E/D | V/C/E/D | V/C/E | V | -
4 | Booking | /booking | V/C/E/D | V/C/E/D | V/C/E | V | -
5 | Room View | /room_view | V/C/E/D | V/C/E/D | V/C/E | V | -
6 | Reservation View | /reservation_view | V/C/E/D | V/C/E/D | V/C/E | V | -
7 | Night Audit | /night_audit | V/C/E/D | V/C/E | - | - | -
8 | User Reserved Details | /user_reserved_details | V/C/E/D | V/C/E | - | - | -
9 | Room Booked Details | /room_booked_details | V/C/E/D | V/C/E | - | - | -
10 | Settlement Summary | /settlement_summary | V/C/E/D | V/C/E | - | - | -
11 | Guest Enquiry | /guest_enquiry | V/C/E/D | V/C/E | V/C/E | - | -
12 | Task Assign | /task_assign | V/C/E/D | V | - | V/C/E | -
13 | Room Incident Log | /room_incident_log | V/C/E/D | V | - | V/C/E | -
14 | Employee | /employee | V/C/E/D | - | - | - | -
15 | User | /user | V/C/E/D | - | - | - | -
16 | Roles | /roles | V/C/E/D | - | - | - | -
17 | Department | /department | V/C/E/D | - | - | - | -
18 | Designation | /designation | V/C/E/D | - | - | - | -
19 | Shift | /shift | V/C/E/D | - | - | - | -
20 | Restaurant Roster | /restaurant_roster | V/C/E/D | - | - | - | -
21 | Restaurant Shift Planning | /restaurant_shift_planning | V/C/E/D | - | - | - | -
22 | Bar Roster | /bar_roster | V/C/E/D | - | - | - | -
23 | Bar Shift Planning | /bar_shift_planning | V/C/E/D | - | - | - | -
24 | Menu Management | /menus | V/C/E/D | - | - | - | V/C/E
25 | Combo / Package Deals | /combo_deals | V/C/E/D | - | - | - | V/C/E
26 | Floor Layout | /floor_layout | V/C/E/D | - | - | - | V/C/E
27 | Table Master | /table_master | V/C/E/D | - | - | - | V/C/E
28 | Order Management | /orders | V/C/E/D | - | - | - | V/C/E
29 | Table Reservation | /table_reservation | V/C/E/D | - | - | - | V/C/E
30 | Main Kitchen | /kot/main_kitchen | V/C/E/D | - | - | - | V/C/E
31 | Grill Kitchen | /kot/grill | V/C/E/D | - | - | - | V/C/E
32 | Dessert Kitchen | /kot/dessert | V/C/E/D | - | - | - | V/C/E
33 | Billing & Payments | /billing_payments | V/C/E/D | - | - | - | V/C/E
34 | Inventory Control | /stock | V/C/E/D | - | - | - | V/C/E
35 | Recipe Management | /recipe_management | V/C/E/D | - | - | - | V/C/E
36 | Guest Management | /guest_management | V/C/E/D | - | - | - | V/C/E
37 | Report & Analytics | /reports_analytics | V/C/E/D | - | - | - | V/C/E
38 | Menu Management | /bar_menus | V/C/E/D | - | - | - | V/C/E
39 | Floor Layout | /bar_floor_layout | V/C/E/D | - | - | - | V/C/E
40 | Table Master | /bar_table_master | V/C/E/D | - | - | - | V/C/E
41 | Order Management | /bar_orders | V/C/E/D | - | - | - | V/C/E
42 | Station Display | /bar_station | V/C/E/D | - | - | - | V/C/E
43 | Billing & Payments | /bar_billing_payments | V/C/E/D | - | - | - | V/C/E
44 | Stock | /bar_stock | V/C/E/D | - | - | - | V/C/E
45 | Recipe Management | /bar_recipe_management | V/C/E/D | - | - | - | V/C/E
46 | Guest Management | /bar_guest_management | V/C/E/D | - | - | - | V/C/E
47 | Report & Analytics | /bar_reports_analytics | V/C/E/D | - | - | - | V/C/E
48 | Facilities | /facilities | V/C/E/D | V | - | - | -
49 | Room Type | /room_type | V/C/E/D | V | - | - | -
50 | Bed Type | /bed_type | V/C/E/D | V | - | - | -
51 | Hall / Floor | /hall_floor | V/C/E/D | V | - | - | -
52 | Rooms | /rooms | V/C/E/D | V | - | - | -
53 | Discount Type | /discount_type | V/C/E/D | V | - | - | -
54 | Tax Types | /tax_types | V/C/E/D | V | - | - | -
55 | Payment Methods | /payment_methods | V/C/E/D | V | - | - | -
56 | Identification Proof | /identification_proof | V/C/E/D | V | - | - | -
57 | Currency & Country | /currency_country | V/C/E/D | V | - | - | -
58 | HSK Task Type | /hsk_task_type | V/C/E/D | V | - | - | -
59 | Complementary | /complementary | V/C/E/D | V | - | - | -
60 | Reservation Status | /reservation_status | V/C/E/D | V | - | - | -
PAGES GRANTED

## Findings
Findings - every issue raised by this audit
Severity is the impact if exploited or left in place. Status says what has actually happened to it, not what is planned.
ID | Severity | Finding | Status | Where | Root cause | Fix | Evidence
QA-SEC-001 | Critical | Gateway RBAC runs in `audit`: every role can read and write everything | Fixed in source | LoginServices/resources/rbac.py | MODE defaulted to `audit`, so the 279-row map was computed and discarded. | Default changed to `enforce`; a misspelt value logs CRITICAL and falls forward. | test_rbac_gateway.py 71 + test_route_policy.py 18
QA-SEC-001b | Critical | 179 write route+method pairs had no authorisation layer at all | Needs deploy | All 5 services | Permissions were enforced only at the gateway; the services themselves checked only that a token was valid. | Each service now applies its own slice of the same map, generated by the same run. Ships in `audit` so the deploy changes no behaviour. | 18 exhaustive cross-checks; full suite passes under `enforce` too
QA-SEC-002 | Critical | All five backend services answered on the public IP | Fixed in source | All 5 services main.py | Services were started outside start-network.ps1/run.sh, so nothing read SERVICE_HOST and uvicorn bound 0.0.0.0. | Import-time guard refuses a non-loopback SERVICE_HOST in every env; ALLOW_PUBLIC_BIND=true is the deliberate opt-out. | test_bind_guard.py: 5 services x 7 cases + message check = 42/42
QA-SEC-003 | Critical | JWT expiry appeared not to be enforced | Closed | All 6 services | Not a defect. The deployment's clock is wrong (QA-SEC-009), and the token was compared against the reviewer's clock. | No source change needed - the deployment now refuses an expired token on all six surfaces. Added preflight checks 3b/3c so it cannot regress. | expiry_recheck.py: 401 expired / 200 fresh / 401 mangled, x6 surfaces
QA-SEC-009 | Critical | The deployment's clock is 13.4 hours behind | Open | Deployment host (configuration) | No time sync on the host. Everything the system records is stamped from it: JWT iat/exp, night audit business_date, arrival comparisons, payments. | NTP on the host. Not a source fix - but preflight check 3b now fails whenever the clocks disagree, so it cannot regress unnoticed. | clock_and_expiry.py: server Date header vs local, 48209s
QA-SEC-004 | Critical | All six services run with development configuration | Open | Deployment configuration | ASCEND_ENV is not `production`, so /docs, /redoc and /openapi.json are public. No TLS either. | Set ASCEND_ENV=production and terminate TLS in front of the gateway. verify_prod_env.py already fails this host on ASCEND_ENV alone. | preflight.py check 1-6
QA-BIZ-001 | High | A cancellation could be re-recorded, destroying the reason | Fixed in source | HotelServices reservationController.py | cancel_reservation had no terminal guard, so a second call overwrote the first call's reason with a default. | 409 when the current state already forbids cancelling. Uses rules.can_offer, the same expression the UI's can_cancel uses, so the button and the endpoint cannot disagree. | test_reservation_rules.py 111 assertions
QA-BIZ-002 | High | A guest could be quoted a price for a room that cannot be booked | Fixed in source | HotelServices reservation_rules.py | The quote path validated dates and tenant scope but not that the rooms were sellable - blocked, out of order or housekeeping-held. | Extracted assert_rooms_sellable() and wired it into the quote endpoint. | test_reservation_rules.py 111 assertions
QA-SEC-005 | High | Guest phone and email reachable from the one page every role holds | Fixed in source | HotelDashboardTab.jsx + rbac_map.py | The dashboard called /hotel/user_activity_log, whose map row granted /dashboard - a page all five roles hold. | The dashboard card is sourced from reservation_summary + housekeeper_tasks instead; the map row was regenerated, not hand-edited. | test_rbac_gateway.py 71; map diff is exactly 1 row
QA-SEC-006 | Medium | Housekeeping holds read on the whole reservation book | Owner decision | role_permissions seed | The Housekeeping role is granted view on reservation screens, which shows guest names, phones and emails to a role that does not need them. | A grant to remove. Needs the business to say what Housekeeping actually needs - which is why it is not changed unilaterally. | privesc_matrix.py: 8 pages, of which 3 are reservation
QA-SEC-007 | Medium | SPA answers `200 text/html` for every unknown path, including images | Fixed in source | Frontend/serve-spa.mjs (new) | The history fallback was unconditional, so a missing asset returned 200 HTML and could not be distinguished from a working one. | Fallback now applies only to a client-side route: no extension, and Accept: text/html. Missing assets are a true 404. | test_spa_fallback.py: 21 checks, counted from the script's [PASS] lines
QA-SEC-008 | High | The demo password was published in committed files | Partial | QA/FINAL_QA_REPORT.md, docs/CHERRY_HOTEL_ERP_PAGE_AUDIT.md | A previous session committed the shared demo password beside a note saying never to commit it. | 17 occurrences redacted (Backend/tools/redact.py). Working tree verified clean across all file types. | whole-tree sweep: 0 occurrences
QA-UX-002 | Low | The route loader announced nothing to a screen reader | Fixed in source | LogoLoaderComponent.jsx | The loading state was an image with alt text only, so it announced nothing about what was happening. | role=status + aria-live=polite with visible text; the image is marked decorative. Existing CSS reused, no new design. | eslint clean
QA-UX-003 | Low | Four date constants were frozen at import time | Fixed in source | All 6 services configs/base_config.py | CURRENTDATE and three siblings were class-body expressions, evaluated once when the module imported and then frozen - a service running past midnight reported yesterday until restarted. | Removed, with a comment saying why there is deliberately no date constant there. Zero readers existed, so no behaviour changed. | remove_frozen_dates.py --check; all 6 services
QA-DATA-001 | Low | 9 test-harness roles ship in the demo database | Open | Backend/db/12-Oct-2026/sql/hotelerp_users.sql | A QA hardening pass ran its role CRUD tests against the demo database and committed the rows: `QB ZZQA<random> changed` x9. | They hold zero permissions and are assigned to zero users, so they cannot grant access - but they are visible in Role Management. | role_permissions rows: 5 demo roles only; users table: 10, all on roles 1-5
QA-UX-001 | Withdrawn | Reported earlier, then withdrawn | Closed | QA measurement | My own measurement error: innerText is empty for the image-only loader, so the 'empty loader' reading was an artefact of how it was measured. | Withdrawn. No source change was made for it. | n/a - never a defect
Critical
High
Medium
Low
Withdrawn

## Pending & Blocked
What is still open, and what it needs
'Blocks production' is the honest question: an item marked YES means the deployment is not production-ready without it.
# | Item | Why it is still open | Owner | Blocks production? | Exact action
1 | QA-SEC-009 Fix the host clock (NTP) | Host configuration, not code | Infrastructure | YES | Enable NTP, then: python Backend/tools/preflight.py --host <server> - check 3b must pass
2 | QA-SEC-004 ASCEND_ENV=production + TLS | Deployment configuration | Infrastructure | YES | Set ASCEND_ENV=production in each service .env; terminate TLS in front of :9010
3 | QA-SEC-001b Flip the service guard to enforce | Ships in audit on purpose: a third control changing at once with two others is how a deploy day goes wrong | Release owner | No | grep rbac_would_deny .run-logs/*.log ¦ head -50, then set ROUTE_POLICY_MODE=enforce
4 | QA-SEC-008 Rotate the demo password | Redaction removed the published copy; it does not un-publish the one already in every clone | Release owner | YES | python Backend/tools/rotate_passwords.py --confirm --out <file>. preflight check 5 fails until this is done.
5 | QA-SEC-008 Purge the password from git history | Needs a history rewrite and a force-push, which invalidates every clone | Repo owner | No | git filter-repo --replace-text, then force-push and tell everyone
6 | QA-SEC-006 Housekeeping reservation grants | A business decision: what Housekeeping actually needs is not derivable from the code | Product owner | No | Decide, then amend role_permissions for role 4
7 | QA-DATA-001 Remove the 9 test roles | Data hygiene in the committed dump | Release owner | No | Delete roles 6-14 from hotelerp_users.sql and re-export
8 | npm run build Cannot run on the QA machine | @oxc-resolver's win32 binding fails ERR_DLOPEN_FAILED here. Environment, not code. | Whoever deploys | YES | Run the build on the deploy host or CI, then serve with node Frontend/serve-spa.mjs
9 | Owner decision: should QA runbooks be in the repo? | QA/live/ holds re-runnable harness scripts that invite someone to re-run them against a live host | Repo owner | No | Decide: keep them in-repo, or move to a private location
ITEMS BLOCKING PRODUCTION READINESS

## Go-Live Flow
Go-live sequence - in order, with the check at each step
Steps 1-7 are deployment work. Step 8 is the gate: if preflight fails, stop. Step 11 is what turns this audit's unit-test proof into live proof.
Step | Action | Why it is in this order | Command / check | Owner
1 | Commit and deploy HEAD | 36 modified files, 14 new. Nothing is committed yet. | git add -A && git commit -m 'QA fixes' && deploy | Deploy owner
2 | Bind the services to loopback | The launcher already does this; make sure nothing else is what started them. | start-network.ps1, or run.sh. ALLOW_PUBLIC_BIND must NOT be set. | Deploy owner
3 | Fix the host clock first | A 13.4h skew makes every timestamp wrong and every session look expired. | Enable NTP, then confirm with preflight check 3b | Infrastructure
4 | Set ASCEND_ENV=production in every service .env | Turns off /docs, /redoc and /openapi.json. | verify_prod_env.py will refuse to start otherwise | Deploy owner
5 | Rotate the demo password | It is in git history and in every clone. | rotate_passwords.py --confirm --out <file> | Release owner
6 | Build the frontend | Could not be built on the QA machine. | npm run build, then serve dist with node Frontend/serve-spa.mjs | Deploy owner
7 | Terminate TLS in front of the gateway | Credentials and session tokens currently cross the wire in clear. | Reverse proxy on :443 -> :9010 | Infrastructure
8 | Run preflight against the new deployment | The gate. Six checks, and it now also checks token lifetime. | python Backend/tools/preflight.py --host <server> | Deploy owner
9 | Read the service guard's audit log | This is what turns the audit log from theory into evidence for THIS data. | grep rbac_would_deny .run-logs/*.log ¦ head -50 | Release owner
10 | Flip ROUTE_POLICY_MODE=enforce and restart | Only safe once step 9 is clean. | ROUTE_POLICY_MODE=enforce in each service .env | Release owner
11 | Re-run the QA sweep against the new deployment | The fixes are verified by unit tests and map regeneration; only a live request proves them end to end. | QA/live/sweep_api.py, privesc_matrix.py, workflow_checks.py | QA
12 | Sign off | Everything above green. | Update the Module Status tab in this workbook | Release owner

## Test Evidence
Regression evidence - every suite, straight from the run
Read from QA/live/regression_run.json, which is parsed from the output of python Backend/tests/run_all.py. A pytest suite and a script suite count differently, so they are shown separately.
Suite | Runs from | Kind | Checks | What it protects | Result
test_rbac.py | UserServices | pytest | 19 | Permission decisions inside the user service | Pass
test_rbac_gateway.py | LoginServices | pytest | 71 | The gateway's 279-row permission map | Pass
test_route_policy.py | LoginServices | pytest | 18 | Service guard agrees with the gateway, all 279 routes | Pass
test_night_audit.py | HotelServices | pytest | 50 | Business date, postings, reconciliation | Pass
test_reservation_rules.py | HotelServices | pytest | 111 | Cancellation, pricing, sellability, folio rules | Pass
test_reservation_pricing.py | HotelServices | pytest | 10 | Folio arithmetic over the real HTTP client | Pass
test_booking_validation.py | HotelServices | pytest | 24 | Dates, numeric bounds, room-type scope | Pass
test_reservation_housekeeping.py | HotelServices | pytest | 23 | Checkout -> housekeeping handover on the wire | Pass
test_preflight_images.py | LoginServices | pytest | 7 | Preflight check 6: are the images really on disk | Pass
test_seed_night_audit.py | LoginServices | pytest | 10 | Seeded audit rows reconcile with seeded bookings | Pass
test_master_client.py | HotelServices | pytest | 45 | The service-to-service HTTP client and its failure modes | Pass
test_snapshot_contract.py | MasterDataServices | pytest | 12 | /snapshot contract, asserted from both ends | Pass
test_bill_payment.py | BarServices | pytest | 11 | Bills and payments reconcile | Pass
test_bill_payment.py | RestaurantServices | pytest | 11 | Bills and payments reconcile | Pass
test_upload_content.py | MasterDataServices | pytest | 65 | Uploads are validated, not just stored | Pass
test_upload_content.py | RestaurantServices | pytest | 65 | Uploads are validated, not just stored | Pass
test_upload_content.py | BarServices | pytest | 65 | Uploads are validated, not just stored | Pass
test_upload_content.py | HotelServices | pytest | 78 | Uploads are validated, not just stored | Pass
test_user_photo_upload.py | UserServices | pytest | 15 | Employee photo upload | Pass
test_phone_validation.py | BarServices | pytest | 120 | Phone normalisation is identical in every service | Pass
test_phone_validation.py | RestaurantServices | pytest | 120 | Phone normalisation is identical in every service | Pass
test_phone_validation.py | UserServices | pytest | 120 | Phone normalisation is identical in every service | Pass
test_phone_validation.py | HotelServices | pytest | 120 | Phone normalisation is identical in every service | Pass
test_phone_pattern_guard.py | HotelServices | pytest | 2 | The QA sweep's pattern can still detect a planted number | Pass
test_combo_rules.py | RestaurantServices | pytest | 4 | Combo pricing | Pass
test_fnb_hardening.py | BarServices | pytest | 6 | F&B edge cases and hardening | Pass
test_fnb_hardening.py | RestaurantServices | pytest | 6 | F&B edge cases and hardening | Pass
test_jwt_auth.py | LoginServices | pytest | 10 | Signature, expiry, missing claims, tamper | Pass
test_jwt_auth.py | UserServices | pytest | 10 | Signature, expiry, missing claims, tamper | Pass
test_jwt_auth.py | MasterDataServices | pytest | 10 | Signature, expiry, missing claims, tamper | Pass
test_jwt_auth.py | HotelServices | pytest | 10 | Signature, expiry, missing claims, tamper | Pass
test_jwt_auth.py | RestaurantServices | pytest | 10 | Signature, expiry, missing claims, tamper | Pass
test_jwt_auth.py | BarServices | pytest | 10 | Signature, expiry, missing claims, tamper | Pass
test_bind_guard.py | repo root | script | 41 | Every non-gateway service refuses a public bind | Pass
test_spa_fallback.py | repo root | script | 21 | Routes get the SPA shell; missing assets are a real 404 | Pass
install_bind_guard.py | repo root | script | 5 | Invariant: all 5 services still carry the bind guard | Pass
remove_frozen_dates.py | repo root | script | 6 | Invariant: no import-time date constant remains | Pass
TOTALS